## M1 1 pallets
job | work_in_parallel | work_type | time_machine_needed | quantity_to_produce | total_time_machine_needed | days_machine_needed
0 | 1 | W3 | 30 | 55 | 4400 | 7.3333
1 | 1 | W2 | 10 | 26 | 1560 | 2.6

## M2 1 pallets
job | work_in_parallel | work_type | time_machine_needed | quantity_to_produce | total_time_machine_needed | days_machine_needed
0 | 1 | W0 | 40 | 50 | 4500 | 7.5
1 | 1 | W2 | 10 | 14 | 840 | 1.4

## M3 2 pallets
job | work_in_parallel | work_type | time_machine_needed | quantity_to_produce | total_time_machine_needed | days_machine_needed
0 | 2 | W4 | 40 | 35 | 4550 | 7.5833
0 | 2 | W4 | 40 | 35 | 4550 | 7.5833
1 | 2 | W1 | 40 | 1 | 130 | 0.21667
1 | 2 | W1 | 40 | 1 | 130 | 0.21667

## M4 3 pallets
job | work_in_parallel | work_type | time_machine_needed | quantity_to_produce | total_time_machine_needed | days_machine_needed
0 | 3 | W1 | 40 | 31 | 5270 | 8.7833
0 | 3 | W1 | 40 | 31 | 5270 | 8.7833
0 | 3 | W1 | 40 | 31 | 5270 | 8.7833